## Dashboard
ColdChainRx Final Project Planning Dashboard
Smart Pharmaceutical Cold-Chain Monitoring and Drug Recall Management System
KPI | Value | Target / Interpretation | Project Timeline Snapshot | Value |  | Risk Category | Count | Average Exposure
Functional Requirements | 18 | 18 FRs with traceability | Project Start | 2026-06-10 |  | Product | 4 | 12.5
Non-Functional Requirements | 10 | 10 measurable NFRs | Target Submission | 2026-07-10 |  | Project | 4 | 10.3
Planned Test Cases | 12 | 12 test cases across 4+ use cases | Tasks Completed | 5 |  | Business | 4 | 10.3
Total Risks | 12 | 12 risks, 4 per category | Tasks In Progress | 4
High/Critical Risks | 8 | Must have mitigation and contingency | Tasks Not Started | 23
Traceability Gaps | 0 | Target = 0 | Average Completion | 24%
Critical Path Tasks | 17 | Must be monitored weekly
Deliverable | Status | Evidence Sheet / File | Milestone | Planned Date | Owner | Evidence
SRS requirements baseline | Ready for Review | Requirements | Topic approval | 2026-06-10 | All Members | Project charter
WBS + Gantt | Ready for Review | WBS_Gantt | Requirements baseline complete | 2026-06-16 | Requirements Lead | FR/NFR register
Risk register + matrix | Ready for Review | Risk_Register / Risk_Matrix | UML design package complete | 2026-06-26 | UML/Design Lead | StarUML exports
Test cases | Ready for Review | Test_Cases | Prototype screenshots ready | 2026-06-30 | Prototype/QA Lead | HTML screenshots
Traceability matrix | Ready for Review | Traceability | Final Word report ready | 2026-07-06 | All Members | SRS + dossier
Screenshot index | Planned | Artifact_Index | Defense rehearsal | 2026-07-08 | All Members | Mock viva notes
HTML prototype | Planned | Prototype files | Final submission | 2026-07-10 | All Members | Word + PowerPoint
StarUML source | Planned | coldchainrx.mdj

## Requirements
ColdChainRx Requirements Register
This sheet is the single requirements baseline used by the Use Cases, Traceability Matrix, Test Cases, and UML design.
FR ID | Functional Requirement | Actor/Source | Priority | Acceptance Criteria | Primary Use Case | Verification | Status
FR-01 | Register a medicine batch with batch number, medicine name, expiry date, supplier, approved temperature range, and QR/GS1 identifier. | Warehouse Manager | Must | The batch cannot be saved unless all mandatory fields are completed and the batch number is unique. | UC-02 | Functional test + data validation | Ready for Review
FR-02 | Create a cold-chain shipment containing one or more registered medicine batches. | Warehouse Manager | Must | The shipment receives a unique shipment ID and initial status 'Prepared'. | UC-03 | Functional test | Ready for Review
FR-03 | Assign a driver and delivery vehicle to a shipment. | Warehouse Manager | Must | A shipment cannot move to 'Dispatched' unless both driver and vehicle are assigned. | UC-04 | Functional test | Ready for Review
FR-04 | Start delivery after the driver confirms pickup. | Delivery Driver | Must | Shipment status changes from 'Prepared' to 'In Transit' with pickup timestamp and driver ID. | UC-05 | Functional test | Ready for Review
FR-05 | Receive temperature and humidity readings from the IoT sensor linked to a shipment. | IoT Temperature Sensor | Must | Each reading is stored with timestamp, sensor ID, shipment ID, temperature, humidity, and battery status. | UC-07 | Integration test | Ready for Review
FR-06 | Detect temperature breaches by comparing readings with the approved temperature range of all medicine batches in the shipment. | Monitoring Service | Must | If readings are outside range for more than 5 continuous minutes, a breach record is created. | UC-08 | Boundary + integration test | Ready for Review
FR-07 | Send breach alerts to the Warehouse Manager and QA Officer. | Monitoring Service | Must | Alert is generated within 10 seconds after breach detection. | UC-18 | Notification test | Ready for Review
FR-08 | Automatically mark affected shipment as Quarantined after a confirmed temperature breach. | Monitoring Service | Must | Quarantined shipments cannot be received as usable stock until QA approval is recorded. | UC-09 | Functional + database state test | Ready for Review
FR-09 | Allow QA Officer to review breach details and release or reject a quarantined shipment. | Quality Assurance Officer | Must | Decision record includes result, reviewer ID, timestamp, and written justification. | UC-10 | Functional test | Ready for Review
FR-10 | Allow Hospital Pharmacist to scan shipment QR code and view shipment status before accepting delivery. | Hospital Pharmacist | Must | Pharmacist cannot accept a shipment with status 'Quarantined' or 'Rejected'. | UC-11 | Negative test | Ready for Review
FR-11 | Allow Hospital Pharmacist to scan each batch QR code during receiving. | Hospital Pharmacist | Must | Batch details, expiry date, and temperature compliance status display within 2 seconds. | UC-12 | Performance + functional test | Ready for Review
FR-12 | Allow Supplier to issue a recall notice for a specific medicine batch. | Supplier | Must | Recall notice includes batch number, reason, severity, issue date, and supplier contact. | UC-13 | Functional test | Ready for Review
FR-13 | Identify all warehouses, shipments, hospitals, and pharmacies that received a recalled batch. | Traceability Service | Must | Affected-location list is generated within 5 seconds for up to 10,000 movement records. | UC-14 | Performance test | Ready for Review
FR-14 | Notify affected users when a recall notice is issued. | Notification Gateway | Must | Notifications are sent to all affected locations within 60 seconds after recall confirmation. | UC-18 | Notification test | Ready for Review
FR-15 | Generate PDF compliance report for selected shipment or batch history. | Warehouse Manager / QA Officer | Should | Report includes shipment timeline, sensor readings, breach records, QA decisions, and receiving status. | UC-15 | Report content test | Ready for Review
FR-16 | Manage user accounts, roles, and account status. | System Administrator | Must | A deactivated user is blocked from logging in immediately after account deactivation. | UC-16 | Security test | Ready for Review
FR-17 | Record audit logs for all critical actions. | Audit Service | Must | Audit log includes actor ID, action type, timestamp, affected object ID, and old/new status. | UC-17 | Audit sampling | Ready for Review
FR-18 | Display operational dashboard showing active shipments, breaches, quarantine cases, pending QA reviews, and recalls. | All Internal Users | Should | Dashboard refreshes automatically at least every 30 seconds. | UC-17 | UI + timing test | Ready for Review
NFR ID | Category | Measurable Requirement | Numeric Target | Verification Method | Traced Features | Status
NFR-01 | Performance | Dashboard data shall display under expected operational load. | <= 3 seconds with 100 concurrent users | Load test with simulated users | FR-18 | Ready for Review
NFR-02 | Sensor Processing | Incoming sensor readings shall be processed promptly. | <= 2 seconds after receipt | Sensor integration simulation | FR-05, FR-06 | Ready for Review
NFR-03 | Security | All user communications shall be encrypted. | 100% HTTPS/TLS traffic | Security configuration inspection | FR-16 | Ready for Review
NFR-04 | Authentication | User accounts shall be protected against repeated failed login attempts. | Lock for 10 minutes after 5 failures | Authentication test case | FR-16 | Ready for Review
NFR-05 | Availability | Core web application shall remain available for operational users. | >= 99.5% monthly availability | Uptime monitoring report | FR-05 to FR-18 | Ready for Review
NFR-06 | Auditability | All critical actions shall be logged. | 100% of critical actions | Audit log sampling | FR-17 | Ready for Review
NFR-07 | Usability | Trained hospital pharmacist shall complete receiving workflow quickly. | <= 3 minutes | User acceptance test | FR-10, FR-11 | Ready for Review
NFR-08 | Data Retention | Sensor readings and audit logs shall be retained. | >= 5 years | Database retention policy review | FR-05, FR-17 | Ready for Review
NFR-09 | Compatibility | Dashboard shall support modern browsers and tablet viewports. | >= 768 px width on Chrome/Edge/Safari/Firefox | Browser compatibility test | FR-18 | Ready for Review
NFR-10 | Business Rule | Unsafe stock shall never enter usable inventory. | 0 quarantined/rejected shipments added to usable stock | Functional + database state test | FR-08, FR-10 | Ready for Review

## WBS_Gantt
ColdChainRx Work Breakdown Structure, Gantt Schedule, Baseline Tracking & Critical Path
Project Start | 2026-06-10 | Target Submission | 2026-07-10 | Calendar | Business/academic days | Last Updated | 2026-06-10
Daily Gantt Timeline (red = critical path, blue = non-critical tasks)
WBS ID | Level | Work Package / Activity | Owner | Start | Duration | Finish | Predecessor | Dep. Type | Milestone | Critical | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Status | % Complete | Evidence / Output | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10
1.0 | 1 | Project Initiation & Scope | All Members | 2026-06-10 | 2 | 2026-06-11 |  | FS | Yes | No | 2026-06-10 | 2026-06-11 |  |  | Completed | 100% | Approved topic and project charter
1.1 | 2 | Topic approval and uniqueness confirmation | Member 1 - Requirements Lead | 2026-06-10 | 1 | 2026-06-10 |  | FS | Yes | No | 2026-06-10 | 2026-06-10 |  |  | Completed | 100% | Instructor approval evidence
1.1.1 | 3 | Submit ColdChainRx proposal | Member 1 - Requirements Lead | 2026-06-10 | 1 | 2026-06-10 |  | FS | No | Yes | 2026-06-10 | 2026-06-10 |  |  | Completed | 100% | Proposal text
1.2 | 2 | Stakeholder and persona analysis | Member 1 - Requirements Lead | 2026-06-11 | 1 | 2026-06-11 | 1.1 | FS | No | No | 2026-06-11 | 2026-06-11 |  |  | Completed | 100% | Persona list
1.2.1 | 3 | Define in-scope / out-of-scope and MoSCoW priorities | Member 1 - Requirements Lead | 2026-06-11 | 1 | 2026-06-11 | 1.1.1 | FS | No | Yes | 2026-06-11 | 2026-06-11 |  |  | Completed | 100% | Scope baseline
2.0 | 1 | Requirements Specification | Member 1 - Requirements Lead | 2026-06-12 | 5 | 2026-06-16 | 1.0 | FS | Yes | No | 2026-06-12 | 2026-06-16 |  |  | In Progress | 70% | SRS requirement section
2.1 | 2 | Draft 18 functional requirements | Member 1 - Requirements Lead | 2026-06-12 | 2 | 2026-06-13 | 1.2 | FS | No | Yes | 2026-06-12 | 2026-06-13 |  |  | In Progress | 80% | FR register
2.1.1 | 3 | Write acceptance criteria for every FR | Member 1 - Requirements Lead | 2026-06-13 | 2 | 2026-06-14 | 2.1 | SS | No | Yes | 2026-06-13 | 2026-06-14 |  |  | In Progress | 60% | Testable acceptance criteria
2.2 | 2 | Define 10 measurable non-functional requirements | Member 1 - Requirements Lead | 2026-06-14 | 2 | 2026-06-15 | 2.1 | FS | No | Yes | 2026-06-14 | 2026-06-15 |  |  | In Progress | 60% | NFR register
2.3 | 2 | Define external interfaces and operating environment | Member 1 - Requirements Lead | 2026-06-15 | 2 | 2026-06-16 | 2.2 | FS | No | No | 2026-06-15 | 2026-06-16 |  |  | Not Started | 0% | Interface section
3.0 | 1 | Project Planning | Member 3 - Prototype/QA Lead | 2026-06-15 | 5 | 2026-06-19 | 2.0 | FS | Yes | No | 2026-06-15 | 2026-06-19 |  |  | Not Started | 0% | WBS, Gantt, risks
3.1 | 2 | Build WBS and Gantt schedule | Member 3 - Prototype/QA Lead | 2026-06-15 | 2 | 2026-06-16 | 2.1 | FS | No | No | 2026-06-15 | 2026-06-16 |  |  | Not Started | 0% | Excel Gantt
3.2 | 2 | Create risk register and risk matrix | Member 3 - Prototype/QA Lead | 2026-06-16 | 2 | 2026-06-17 | 3.1 | SS | No | No | 2026-06-16 | 2026-06-17 |  |  | Not Started | 0% | Risk register
3.3 | 2 | Create traceability matrix template | Member 3 - Prototype/QA Lead | 2026-06-18 | 2 | 2026-06-19 | 2.1.1 | FS | No | Yes | 2026-06-18 | 2026-06-19 |  |  | Not Started | 0% | Traceability matrix
4.0 | 1 | System Design Package | Member 2 - UML/Design Lead | 2026-06-18 | 9 | 2026-06-26 | 2.0 | FS | Yes | No | 2026-06-18 | 2026-06-26 |  |  | Not Started | 0% | UML dossier
4.1 | 2 | Context diagram and interface block diagram | Member 2 - UML/Design Lead | 2026-06-18 | 2 | 2026-06-19 | 2.3 | FS | No | No | 2026-06-18 | 2026-06-19 |  |  | Not Started | 0% | Fig01-Fig02
4.2 | 2 | Use case diagram with 15+ use cases | Member 2 - UML/Design Lead | 2026-06-19 | 2 | 2026-06-20 | 2.1 | FS | No | Yes | 2026-06-19 | 2026-06-20 |  |  | Not Started | 0% | Fig03
4.3 | 2 | Four activity diagrams with swimlanes | Member 2 - UML/Design Lead | 2026-06-20 | 3 | 2026-06-22 | 4.2 | FS | No | No | 2026-06-20 | 2026-06-22 |  |  | Not Started | 0% | Fig04-Fig07
4.4 | 2 | Class diagram with multiplicities and typed attributes | Member 2 - UML/Design Lead | 2026-06-22 | 3 | 2026-06-24 | 4.2 | FS | No | Yes | 2026-06-22 | 2026-06-24 |  |  | Not Started | 0% | Fig08
4.5 | 2 | Four sequence diagrams matching class diagram | Member 2 - UML/Design Lead | 2026-06-24 | 3 | 2026-06-26 | 4.4 | FS | No | Yes | 2026-06-24 | 2026-06-26 |  |  | Not Started | 0% | Fig09-Fig12
5.0 | 1 | Prototype & Testing | Member 3 - Prototype/QA Lead | 2026-06-24 | 8 | 2026-07-01 | 4.0 | FS | Yes | No | 2026-06-24 | 2026-07-01 |  |  | Not Started | 0% | HTML screens and tests
5.1 | 2 | Build HTML/CSS/JS prototype skeleton | Member 3 - Prototype/QA Lead | 2026-06-24 | 2 | 2026-06-25 | 2.3 | FS | No | Yes | 2026-06-24 | 2026-06-25 |  |  | Not Started | 0% | Prototype index.html
5.2 | 2 | Create dashboard, tracking, breach, quarantine, recall screens | Member 3 - Prototype/QA Lead | 2026-06-26 | 3 | 2026-06-28 | 5.1 | FS | No | Yes | 2026-06-26 | 2026-06-28 |  |  | Not Started | 0% | Prototype screenshots
5.3 | 2 | Design 12 test cases for four use cases | Member 3 - Prototype/QA Lead | 2026-06-27 | 2 | 2026-06-28 | 3.3 | FS | No | Yes | 2026-06-27 | 2026-06-28 |  |  | Not Started | 0% | Test case register
5.4 | 2 | Run prototype checks and capture screenshots | Member 3 - Prototype/QA Lead | 2026-06-29 | 2 | 2026-06-30 | 5.2 | FS | No | No | 2026-06-29 | 2026-06-30 |  |  | Not Started | 0% | Screenshot package
6.0 | 1 | Report, Presentation & Defense | All Members | 2026-06-30 | 11 | 2026-07-10 | 5.0 | FS | Yes | No | 2026-06-30 | 2026-07-10 |  |  | Not Started | 0% | Final Word and PPT
6.1 | 2 | Assemble Word SRS and design dossier | Member 1 - Requirements Lead | 2026-06-30 | 4 | 2026-07-03 | 4.5,5.3 | FS | No | Yes | 2026-06-30 | 2026-07-03 |  |  | Not Started | 0% | Final report draft
6.2 | 2 | Insert screenshots, captions, figures, and references | Member 1 - Requirements Lead | 2026-07-03 | 3 | 2026-07-05 | 6.1 | FS | No | Yes | 2026-07-03 | 2026-07-05 |  |  | Not Started | 0% | Formatted report
6.3 | 2 | Create PowerPoint defense presentation | Member 3 - Prototype/QA Lead | 2026-07-04 | 3 | 2026-07-06 | 6.1 | SS | No | No | 2026-07-04 | 2026-07-06 |  |  | Not Started | 0% | Presentation deck
6.4 | 2 | Run cross-artifact consistency review | All Members | 2026-07-06 | 2 | 2026-07-07 | 6.2 | FS | No | Yes | 2026-07-06 | 2026-07-07 |  |  | Not Started | 0% | Review checklist
6.5 | 2 | Mock defense and final corrections | All Members | 2026-07-08 | 2 | 2026-07-09 | 6.4 | FS | No | Yes | 2026-07-08 | 2026-07-09 |  |  | Not Started | 0% | Defense notes
6.6 | 2 | Final submission package | All Members | 2026-07-10 | 1 | 2026-07-10 | 6.5 | FS | Yes | Yes | 2026-07-10 | 2026-07-10 |  |  | Not Started | 0% | Submitted files
Formulas:
Finish = [Start]+[Duration]-1
Baseline Finish = [Baseline Start]+[Duration]-1

## Risk_Register
ColdChainRx Risk Register - Product, Project, and Business Risks
Risk Exposure (RE) = Probability (1-5) × Impact (1-5). Residual RE is calculated after mitigation.
Risk ID | Category | Risk Event | Probability | Impact | Exposure | Rating | Trigger / Early Indicator | Owner | Mitigation Plan | Contingency Plan | Residual P | Residual I | Residual Exposure
R-01 | Product | IoT sensor sends inaccurate temperature readings | 3 | 5 | 15 | High | Sudden abnormal readings or repeated calibration drift | Member 3 - Prototype/QA Lead | Validate readings against safe physical limits and require repeated confirmation before breach classification. | Mark shipment as Sensor Suspected and require manual QA inspection before release. | 2 | 4 | 8
R-02 | Product | Temperature breach is not detected within the required time | 2 | 5 | 10 | High | Monitoring service queue delay or missing readings | Member 2 - UML/Design Lead | Unit-test threshold logic and simulate continuous out-of-range readings during integration testing. | Generate daily exception report from raw sensor history for QA review. | 1 | 5 | 5
R-03 | Product | Recall traceability misses an affected hospital or pharmacy | 3 | 5 | 15 | High | Incomplete batch movement record or missing receive confirmation | Member 1 - Requirements Lead | Make batch movement audit logs mandatory before shipment status can close. | Notify all locations that received shipments from the same supplier during the risk period. | 2 | 5 | 10
R-04 | Product | Quarantined shipment is accidentally accepted into usable stock | 2 | 5 | 10 | High | Receiving attempt on quarantined shipment | Member 3 - Prototype/QA Lead | Enforce database state rule: Quarantined/Rejected cannot transition directly to Usable Stock. | Lock receiving workflow and require administrator/QA investigation. | 1 | 5 | 5
R-05 | Project | UML diagrams become inconsistent with requirements | 3 | 4 | 12 | High | Unmapped FR or lifeline not present in class diagram | Member 2 - UML/Design Lead | Maintain traceability matrix from the beginning and review it after every diagram update. | Schedule a final cross-artifact correction sprint before submission. | 2 | 3 | 6
R-06 | Project | HTML prototype takes longer than planned | 3 | 3 | 9 | Medium | Incomplete prototype pages by Week 4 | Member 3 - Prototype/QA Lead | Limit prototype to the core pages needed for evidence and screenshots. | Use static mock data and reduce animation/interactive extras. | 2 | 2 | 4
R-07 | Project | Team contribution evidence is insufficient | 2 | 4 | 8 | Medium | No GitHub commits or unclear contribution log | All Members | Assign deliverables per member and commit source files regularly. | Add signed contribution table and defense notes for each member. | 1 | 3 | 3
R-08 | Project | Gantt schedule slips because diagram work is underestimated | 3 | 4 | 12 | High | Activity/sequence diagrams not ready by planned date | Member 2 - UML/Design Lead | Start diagrams after FR baseline and reuse shared class names consistently. | Reduce non-critical diagram complexity while keeping UML notation correct. | 2 | 3 | 6
R-09 | Business | Hospitals reject the workflow because receiving adds extra steps | 3 | 4 | 12 | High | User feedback says receiving workflow is too slow | Member 1 - Requirements Lead | Use QR-based receiving and keep the normal safe-shipment flow under 3 minutes. | Add quick-receive path for safe shipments with full audit logging. | 2 | 3 | 6
R-10 | Business | Supplier batch data format is incompatible | 3 | 3 | 9 | Medium | Supplier files lack required fields or use different formats | Member 2 - UML/Design Lead | Design supplier adapter and validate required fields before import. | Allow manual/CSV recall entry for urgent cases. | 2 | 2 | 4
R-11 | Business | Regulatory data retention period changes | 2 | 4 | 8 | Medium | New GDP or health data retention guidance | Member 1 - Requirements Lead | Make retention period configurable and document data retention NFR. | Update retention setting and regenerate compliance policy. | 1 | 3 | 3
R-12 | Business | Notification provider outage delays breach or recall alerts | 3 | 4 | 12 | High | SMS/email API timeout or error code | Member 3 - Prototype/QA Lead | Use retry queue and support both email and SMS channels. | Display alert banner inside dashboard and export call list for manual contact. | 2 | 3 | 6

## Risk_Matrix
ColdChainRx Risk Matrix - Probability × Impact
Cells count risks by Probability and Impact using formulas from the Risk_Register sheet.
| Probability \ Impact | 1 | 2 | 3 | 4 | 5 | Risk Summary | Formula
| 5 | 0 | 0 | 0 | 0 | 0 | Total risks | 12
| 4 | 0 | 0 | 0 | 0 | 0 | Product risks | 4
| 3 | 0 | 0 | 2 | 4 | 2 | Project risks | 4
| 2 | 0 | 0 | 0 | 2 | 2 | Business risks | 4
| 1 | 0 | 0 | 0 | 0 | 0 | High or Critical risks | 8
[7 empty] | Average exposure | 11

## Test_Cases
ColdChainRx Test Case Register
All test cases include FR traceability, preconditions, inputs, execution steps, expected result, actual result placeholder, verdict, and positive/negative/boundary/performance classification.
TC ID | Use Case | FR ID | Test Type | Preconditions | Input Data | Execution Steps | Expected Result | Actual Result | Verdict | Priority | Owner
TC-01 | UC-03 Create Shipment | FR-02 | Positive | Warehouse Manager is logged in; two valid batches exist. | Batch B-INS-044; Batch B-VAC-210; Sensor S-100; Driver D-07 | Open Create Shipment, select batches, link sensor, assign driver, save. | Shipment is created with unique ID and status Prepared. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-02 | UC-03 Create Shipment | FR-03 | Negative | Warehouse Manager is logged in; no sensor selected. | Batch B-VAC-210; Driver D-07; Sensor blank | Try to save shipment without linking sensor. | System blocks save and displays 'Sensor is required before dispatch'. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-03 | UC-08 Detect Breach | FR-06 | Positive | Shipment has approved range 2°C to 8°C. | Temperature readings: 4.2°C, 4.4°C, 4.1°C | Submit readings through simulated sensor gateway. | Readings are stored; no breach is created; shipment remains In Transit. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-04 | UC-08 Detect Breach | FR-06 | Boundary | Shipment has approved range 2°C to 8°C. | Temperature reading exactly 8.0°C | Submit boundary reading through sensor gateway. | Reading is accepted as within range and no breach is created. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-05 | UC-08 Detect Breach | FR-06, FR-08 | Negative | Shipment has approved range 2°C to 8°C. | Temperature = 9.5°C for more than 5 continuous minutes | Submit repeated out-of-range readings over breach window. | Breach record is created; shipment status changes to Quarantined. | To be recorded during execution | Not Run | Critical | Member 3 - Prototype/QA Lead
TC-06 | UC-18 Send Notification | FR-07 | Integration | Confirmed breach exists for active shipment. | Breach ID BR-1004; recipients QA-01 and WM-01 | Trigger breach notification service. | Warehouse Manager and QA Officer receive alert within 10 seconds. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-07 | UC-11 Receive Shipment | FR-10 | Positive | Hospital Pharmacist is logged in; shipment status is In Transit and no active breach. | Shipment QR SH-2026-004 | Scan QR code on receiving page and press Accept. | Shipment is accepted and status changes to Received. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-08 | UC-11 Receive Shipment | FR-10 | Negative | Shipment status is Quarantined. | Shipment QR SH-2026-009 | Scan QR code and press Accept. | System prevents acceptance and displays quarantine warning. | To be recorded during execution | Not Run | Critical | Member 3 - Prototype/QA Lead
TC-09 | UC-12 Scan Batch | FR-11 | Negative | Hospital receiving page is open. | Unknown QR code B-UNKNOWN-999 | Scan unknown batch QR code. | System displays 'Batch not found' and prevents receiving confirmation. | To be recorded during execution | Not Run | Medium | Member 3 - Prototype/QA Lead
TC-10 | UC-13 Issue Recall | FR-12 | Positive | Supplier is logged in; batch B-VAC-210 exists. | Batch B-VAC-210; reason: potency defect; severity: High | Create recall notice and confirm. | Recall notice is saved with issue date, severity, reason, and supplier contact. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-11 | UC-14 Trace Recalled Batch | FR-13 | Performance | 10,000 movement records exist in test dataset. | Recall ID RC-2026-002 for B-VAC-210 | Run affected-location trace. | System returns affected locations within 5 seconds. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead
TC-12 | UC-18 Send Recall Notifications | FR-14 | Integration | Recall has affected locations list. | Affected users at 12 hospitals/pharmacies | Confirm recall notification sending. | All affected locations receive notification within 60 seconds or are listed in retry queue. | To be recorded during execution | Not Run | High | Member 3 - Prototype/QA Lead

## Traceability
ColdChainRx Requirements Traceability Matrix
Every FR must link forward to a use case, class(es), sequence diagram, activity diagram where relevant, test case(s), prototype screen, and current gap status.
FR ID | Use Case | Class(es) | Sequence Diagram | Activity Diagram | Test Case(s) | Prototype Screen | Trace Status | Notes
FR-01 | UC-02 Register Batch | MedicineBatch, Supplier, AuditLog | SD-01 Create Shipment | AD-01 Shipment Creation | TC-01 | Batch Registration / Create Shipment | Complete | Batch data feeds shipment creation.
FR-02 | UC-03 Create Shipment | Shipment, MedicineBatch, ColdBox, AuditLog | SD-01 Create Shipment | AD-01 Shipment Creation | TC-01 | Create Shipment | Complete | Core warehouse workflow.
FR-03 | UC-04 Assign Driver | Shipment, Driver, Vehicle | SD-01 Create Shipment | AD-01 Shipment Creation | TC-02 | Create Shipment | Complete | Driver assignment blocks dispatch if missing.
FR-04 | UC-05 Start Delivery | Shipment, Driver, AuditLog | SD-01 Create Shipment | AD-01 Shipment Creation | TC-01 | Shipment Tracking | Complete | Status transition to In Transit.
FR-05 | UC-07 Receive Sensor Reading | SensorReading, ColdBox, Shipment | SD-02 Detect Breach | AD-02 Breach Handling | TC-03, TC-04 | Tracking | Complete | Raw readings stored for reporting.
FR-06 | UC-08 Detect Breach | SensorReading, TemperatureBreach, Shipment | SD-02 Detect Breach | AD-02 Breach Handling | TC-03, TC-04, TC-05 | Breach Alert | Complete | Boundary cases trace to breach rules.
FR-07 | UC-18 Send Notification | TemperatureBreach, Notification, User | SD-02 Detect Breach | AD-02 Breach Handling | TC-06 | Breach Alert | Complete | Breach alert timing verified.
FR-08 | UC-09 Quarantine Shipment | Shipment, QuarantineCase, TemperatureBreach | SD-02 Detect Breach | AD-02 Breach Handling | TC-05, TC-08 | Quarantine Review | Complete | Business rule prevents unsafe receiving.
FR-09 | UC-10 Review Quarantine | QuarantineCase, QAOfficer, AuditLog | SD-02 Detect Breach | AD-02 Breach Handling | TC-08 | Quarantine Review | Complete | QA decision requires justification.
FR-10 | UC-11 Receive Shipment | Shipment, HospitalPharmacist, AuditLog | SD-03 Receive Shipment | AD-03 Hospital Receiving | TC-07, TC-08 | Hospital Receiving | Complete | Acceptance blocked for unsafe states.
FR-11 | UC-12 Scan Batch QR | MedicineBatch, Shipment, HospitalPharmacist | SD-03 Receive Shipment | AD-03 Hospital Receiving | TC-09 | Hospital Receiving | Complete | Batch verification step.
FR-12 | UC-13 Issue Recall | RecallNotice, Supplier, MedicineBatch | SD-04 Issue Recall | AD-04 Drug Recall | TC-10 | Drug Recall | Complete | Supplier-originated recall.
FR-13 | UC-14 Trace Locations | RecallNotice, TraceabilityService, Shipment | SD-04 Issue Recall | AD-04 Drug Recall | TC-11 | Drug Recall | Complete | Performance-traced to 10,000 records.
FR-14 | UC-18 Send Recall Notifications | Notification, RecallNotice, User | SD-04 Issue Recall | AD-04 Drug Recall | TC-12 | Drug Recall | Complete | Retry queue acceptable for failed sends.
FR-15 | UC-15 Generate Report | ComplianceReport, Shipment, SensorReading | SD-04 Issue Recall | AD-04 Drug Recall | TC-11 | Reports | Complete | Report uses traceability data.
FR-16 | UC-16 Manage Users | User, SystemAdministrator, AuditLog | SD-03 Receive Shipment | N/A | TC-07 | Admin/User Management | Complete | Login/security pages in prototype.
FR-17 | UC-17 Audit Logs | AuditLog, User, Shipment | SD-02 Detect Breach | AD-02 Breach Handling | TC-05, TC-10 | Audit Log / Reports | Complete | Critical action logging.
FR-18 | UC-17 View Dashboard | Shipment, TemperatureBreach, QuarantineCase, RecallNotice | SD-02 Detect Breach | AD-02 Breach Handling | TC-03, TC-05 | Dashboard | Complete | Dashboard refresh traced to NFR-01.

## Resources
ColdChainRx Resource Plan & Individual Contribution Baseline
Resource ID | Placeholder Name | Project Role | Primary Responsibility | Secondary Responsibility | Key Evidence | Planned Hours | Actual Hours
RS-01 | Member 1 | Requirements Lead | Problem statement, scope, FR/NFR register, references | Traceability review | Word section drafts + requirements commits | 28
RS-02 | Member 2 | UML / Design Lead | StarUML diagrams, context/interface diagrams, class and sequence consistency | SRS design descriptions | Diagram source files + exported images | 30
RS-03 | Member 3 | Prototype & QA Lead | HTML prototype, test cases, risk register, Gantt updates | PowerPoint assembly | GitHub commits + screenshots | 30
RS-04 | All Members | Defense Team | Final review, mock viva, consistency check | Submission packaging | Signed contribution log | 12
Contribution Evidence Checklist | Status
GitHub repository created | Planned
Each member has at least 5 meaningful commits | Planned
Diagram source files retained | Planned
Excel planning package retained | Planned
Prototype screenshots included in final report | Planned
Signed contribution log included | Planned

## Artifact_Index
ColdChainRx Screenshot & Deliverable Index
Use this sheet to track every screenshot/source file that will be inserted into the final Word report and PowerPoint.
Figure ID | Artifact Name | Tool | Source File | Screenshot File | Report Section | Status | Notes
Fig-01 | System Context Diagram | StarUML/draw.io | context_diagram | Fig01_Context_Diagram.png | 5.1 | Planned | Single process + external entities + labelled data flows
Fig-02 | External Interface Block Diagram | draw.io/PowerPoint | interface_block | Fig02_Interface_Block_Diagram.png | 2.2 | Planned | Browser, API, DB, sensor, GPS, notifications
Fig-03 | Use Case Diagram | StarUML | coldchainrx.mdj | Fig03_Use_Case_Diagram.png | 5.2 | Planned | At least 15 use cases
Fig-04 | Activity Diagram - Shipment Creation | StarUML | coldchainrx.mdj | Fig04_AD_Create_Shipment.png | 5.3 | Planned | Swimlanes: Warehouse Manager, System, Sensor Gateway
Fig-05 | Activity Diagram - Temperature Breach Handling | StarUML | coldchainrx.mdj | Fig05_AD_Temperature_Breach.png | 5.3 | Planned | Decision nodes and QA branch
Fig-06 | Activity Diagram - Hospital Receiving | StarUML | coldchainrx.mdj | Fig06_AD_Hospital_Receiving.png | 5.3 | Planned | Accept/reject/quarantine states
Fig-07 | Activity Diagram - Drug Recall | StarUML | coldchainrx.mdj | Fig07_AD_Drug_Recall.png | 5.3 | Planned | Trace and notify flow
Fig-08 | Class Diagram | StarUML | coldchainrx.mdj | Fig08_Class_Diagram.png | 5.4 | Planned | Typed attributes, methods, multiplicities
Fig-09 | Sequence Diagram - Create Shipment | StarUML | coldchainrx.mdj | Fig09_SD_Create_Shipment.png | 5.5 | Planned | Lifelines match class diagram
Fig-10 | Sequence Diagram - Detect Breach | StarUML | coldchainrx.mdj | Fig10_SD_Detect_Breach.png | 5.5 | Planned | Includes alt fragment for breach/no breach
Fig-11 | Sequence Diagram - Receive Shipment | StarUML | coldchainrx.mdj | Fig11_SD_Receive_Shipment.png | 5.5 | Planned | Includes rejected/quarantined branch
Fig-12 | Sequence Diagram - Issue Recall | StarUML | coldchainrx.mdj | Fig12_SD_Issue_Recall.png | 5.5 | Planned | Includes loop over affected locations
Fig-13 | Gantt Chart | Excel | ColdChainRx_Planning_Package.xlsx | Fig13_Gantt_Chart.png | 4.1 | Planned | Screenshot from WBS_Gantt
Fig-14 | Risk Matrix | Excel | ColdChainRx_Planning_Package.xlsx | Fig14_Risk_Matrix.png | 4.2 | Planned | Screenshot from Risk_Matrix
Fig-15 | Login Screen | HTML Prototype | index.html | Fig15_Login_Screen.png | Prototype | Planned | Security entry point
Fig-16 | Dashboard Screen | HTML Prototype | index.html | Fig16_Dashboard_Screen.png | Prototype | Planned | KPIs and alert summary
Fig-17 | Shipment Tracking Screen | HTML Prototype | index.html | Fig17_Tracking_Screen.png | Prototype | Planned | Temperature timeline
Fig-18 | Temperature Breach Alert Screen | HTML Prototype | index.html | Fig18_Breach_Alert_Screen.png | Prototype | Planned | Critical workflow evidence
Fig-19 | Quarantine Review Screen | HTML Prototype | index.html | Fig19_Quarantine_Review_Screen.png | Prototype | Planned | QA decision screen
Fig-20 | Drug Recall Screen | HTML Prototype | index.html | Fig20_Recall_Screen.png | Prototype | Planned | Recall traceability evidence

## Lists_References
ColdChainRx Planning Package - Controlled Lists & References
Priority | Status | Risk Category | Risk Rating | Test Type | Owners | Source | URL | Use in project
Must | Not Started | Product | Low | Positive | Member 1 - Requirements Lead | CDC Vaccine Storage and Handling | https://www.cdc.gov/vaccines/hcp/storage-handling/index.html | Problem statement and cold-chain importance
Should | In Progress | Project | Medium | Negative | Member 2 - UML/Design Lead | WHO Technical Report Series 961 Annex 9 | https://www.who.int/publications/i/item/WHO-TRS-961 | Time and temperature sensitive pharmaceutical products
Could | Ready for Review | Business | High | Boundary | Member 3 - Prototype/QA Lead | WHO Good Storage and Distribution Practices | https://www.who.int/publications/i/item/9789240014722 | GDP compliance background
Won't | Completed |  | Critical | Performance | All Members | EMA Good Distribution Practice | https://www.ema.europa.eu/en/human-regulatory-overview/post-authorisation/compliance-post-authorisation/good-distribution-practice | Regulatory constraints
| Deferred |  |  | Security | Instructor | GS1 Healthcare Standards | https://www.gs1.org/industries/healthcare/standards | Batch/QR/traceability interface
|  |  |  | Integration |  | OWASP Top 10 | https://owasp.org/Top10/ | Security NFRs and risk analysis
[6 empty] | NIST Digital Identity Guidelines | https://pages.nist.gov/800-63-3/ | Authentication controls
[6 empty] | OMG UML Specification | https://www.omg.org/spec/UML/ | UML notation reference